## Sheet1
ID | Title | Priority | Estimate(hr) | Desc | Accesptance crit
1 | Install Unity on laptop | M | 1 | unstall unity on latop | can start unity on laptop
2 | Create project | M | 1 | Create a new unity project | can open project
3 | Create gitlab project | M | 1 | Create gitlab page for project | gitlab project exists
4 | Populate gitlab with backlog | M | 1 | Have all backlog ideas in gitlab | All backlog items are on gitlab
5 | Create quadratic spline tool in unity | M | 1 | Follow tutorial to create spline tool | Splines can be created with tool in unity
6 | Integrate spline tool with mesh renderer | M | 2 | Make the spline tool render as a basic mesh | Spline tool creates meshes and updates them
7 | Recreate paper efficent shader | M | 2 | Recreate spline shader described in paper | Spline renders as spline and not mesh (curved edges)
8 | Create cubic spline tool | S | 2 | Follow tutorial to create spline tool | Spline tools allows for the creation of cubic curves
9 | Recreate paper efficent shader (cubic) | S | 2 | Recreate spline shader described in paper with tesselation shader | Cubic splines render with cuvred edges
10 | Integrate shader to lighting pass | S | 2 | Allow for the spline to create shadows | Shadows are cast from spline shapes
11 | Control shadow strenght | C | 2 | Allow for shadows cast from spline to weaken or remove shadows | Spline can remove shadow
12 | Create system to animated spline depending on light direction | C | 2 | Allow for system to sample animations based on direction | Light direction now changes the shape and shade of spline
13 | Animate example spline | C | 1 | Create example spline shadow shading mesh | Can play example realtime
14 | Make playable controller | C | 2 | Create a controllable player character with spline shadow | Users can now control a spline